BUILD PLAN

SkillForge AI

AI-Powered Employee Skill Assessment Platform

Execution Plan • Phase 1 Hyper-MVP to Phase 3 SaaS Launch

| Document ID | SF-BUILD-PLAN-2026-001 |
| --- | --- |
| Version | v1.0 |
| Date | 2026-04-18 |
| Prepared By | Ashish Kumar Satyam (TechDigital WishTree) |
| Prepared For | Qualtech |
| Classification | Internal — Confidential |

⚠ INTERNAL / CONFIDENTIAL — Not for external distribution

# 1. Document Information

| Field | Value |
| --- | --- |
| Document Name | SkillForge AI — Build Plan |
| Document ID | SF-BUILD-PLAN-2026-001 |
| Version | v1.0 |
| Date | 2026-04-18 |
| Owner | Ashish Kumar Satyam |
| Stakeholders | Qualtech Product + Engineering leadership, HR Lead, Security Lead |
| Classification | Internal — Confidential |

# 2. Version History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| v1.0 | 2026-04-18 | Ashish Kumar Satyam | Initial execution plan — hyper-MVP + full Phase 1 + Phase 2/3 outlines |

# 3. Executive Summary

SkillForge AI must support the Qualtech April–June 2026 appraisal cycle, with employee assessments due by end of May 2026. From today (2026-04-18), we have approximately six calendar weeks — equivalent to three two-week sprints — before the appraisal window closes.

This plan defines a three-track build: a Hyper-MVP (Weeks 1–6) delivering only the assessment flow needed to run the cycle, a Full Phase 1 (Weeks 1–16) delivering all P0 and P1 features from the strategic plan §4.1, and a Phase 2+3 roadmap (Weeks 17–48) covering AI-powered evaluation and SaaS productization per plan §4.2 and §4.3.

All 10 open architectural decisions (captured in OPEN_DECISIONS.md) must be resolved during the two-day Architecture Workshop on 2026-04-20 and 2026-04-21. Sprint 0 (Week 0) delivers a fully running dev environment by 2026-04-24 so that Sprint 1 execution begins Monday 2026-04-27.

# 4. Dashboard View

● Hyper-MVP On Track    ● 10 Decisions Open    ● Team Not Yet Assembled

| Metric | Current | Target (Sprint 3) | Status |
| --- | --- | --- | --- |
| Person-days committed (Hyper-MVP) | 95 / 270 | 95 / 270 used | ● Healthy buffer |
| P0 features locked | 6 / 6 scoped | 6 deployed | ● Scoped |
| Open architectural decisions | 10 | 0 | ● Must close by 2026-04-21 |
| Team assembled | Pending | 9–10 FTE | ● At risk |

# 5. Completed Work

Pre-sprint foundation (2026-04-18):

| Artifact | Description | Version | Date |
| --- | --- | --- | --- |
| Strategic Plan DOCX | Product vision, scope, stakeholders, success criteria | v1.0 | 2026-04-01 |
| .claude/ setup | 8 project skills + 5 hooks + settings.json + CLAUDE.md | v1.0 | 2026-04-18 |
| Project memory files | 9 memory files covering overview, phases, tech stack, data model, security, feedback | v1.0 | 2026-04-18 |
| BUILD_PLAN.md | This document — 3-track execution plan | v1.0 | 2026-04-18 |
| OPEN_DECISIONS.md | 10 decisions blocking Sprint 1 kickoff | v1.0 | 2026-04-18 |
| Sprint 0 Checklist | Day-by-day checklist for Week 0 foundation | v1.0 | 2026-04-18 |

# 6. Work in Progress

| Feature | Description | Owner | Expected Completion |
| --- | --- | --- | --- |
| Architecture Workshop | Resolve 10 open decisions, draft ADRs | Tech Lead | 2026-04-21 |
| Repo scaffold | Monorepo with apps/ services/ packages/ infra/ prompts/ | Tech Lead + DevOps | 2026-04-22 |
| CI/CD pipeline | GitHub Actions with typecheck/lint/test/build/deploy | DevOps | 2026-04-23 |
| Design system | shadcn/ui tokens, Figma file, wireframes for Sprint 1 screens | UI/UX + FE Lead | 2026-04-24 |
| DB schema v0 + auth skeleton | Core entities, RBAC, JWT flow | BE Lead | 2026-04-24 |

# 7. Pending Items

| Item | Description | Priority | Remarks |
| --- | --- | --- | --- |
| Team assembly | Allocate/hire 9-10 FTEs per plan §5.1 | P0 | Blocking Sprint 0 start |
| Qualtech IdP discovery | Confirm Azure AD / Okta / other; SAML/OIDC capability | P0 | Needed for D9 Auth decision |
| Appraisal-system export spec | Column layout for CSV export Qualtech HR will consume | P0 | Needed for Sprint 3 |
| Pilot user list | 20 employees + 5 managers for UAT | P0 | Needed for Sprint 3 |
| Competency framework content | Actual AI maturity levels + role mappings for Qualtech | P0 | Needed for Sprint 1 seed |

# 8. Future Roadmap

| Phase | Feature Bucket | Timeline | Effort (person-days) |
| --- | --- | --- | --- |
| Phase 1 — Hyper-MVP | Self-assessment + manager scoring + CSV export | Weeks 1–6 | ~95 |
| Phase 1 — Fast-follow | Dashboards, SSO, notifications, reporting | Weeks 7–16 | ~72 |
| Phase 2 | AI analysis, peer review, HRMS integration, mobile, learning paths, bias detection | Weeks 17–32 | 165 |
| Phase 3 | Multi-tenant provisioning, billing, marketplace, SOC 2 prep, 10K-user scale | Weeks 33–48 | 150 |

# 9. Upcoming Deliveries

| Milestone | Features | Planned Release |
| --- | --- | --- |
| Sprint 0 done | Dev environment operational | 2026-04-24 (Fri) |
| Sprint 1 done | Auth + users + framework + HR admin UI | 2026-05-01 (Fri) |
| Sprint 2 done | Self-assessment end-to-end, artifact upload, reminders | 2026-05-15 (Fri) |
| Sprint 3 done | Manager scoring, composite score, CSV export, pilot UAT | 2026-05-29 (Fri) |
| Hyper-MVP Production | Qualtech runs appraisal cycle on SkillForge | 2026-06-01 (Mon) |
| Full Phase 1 | All P0/P1 Phase-1 features delivered | 2026-08-08 (Week 16) |
| Phase 2 Production | AI-assisted evaluation live | 2026-11-28 (Week 32) |
| Phase 3 — First external client | Qualtech + 1 external pilot | 2027-03-20 (Week 48) |

# 10. Risks & Dependencies

| Risk | Severity | Mitigation |
| --- | --- | --- |
| 6-week MVP window may not absorb all P0 | High | Hyper-MVP strips to 6 features; dashboards deferred to Sprint 4–5 |
| Team not yet assembled | High | Escalate to engineering leadership immediately; interim Tech Lead by 2026-04-19 minimum |
| AI hallucination risk in Phase 2 | High | Manager override mandatory; confidence thresholds; fallback to manual |
| HRMS integration complexity | Medium | Phase 1 uses CSV; API integration starts with 2-week discovery in Sprint 9 |
| Tenant data isolation leak | High | sf-tenant-check skill + pre-edit hook enforce org_id filters from Day 1 |
| PII leak via Claude API | High | pre-edit-prompt-pii hook blocks raw PII in prompt files |
| Qualtech IdP unknown | Medium | Kickoff discovery meeting in Day 1 of Sprint 0 |
| Scope creep | Medium | P0/P1/P2 discipline; change requests become ADRs; no feature merges without ticket |

# 11. Architecture Overview

Stack (from plan §3.2 and reference_tech_stack memory):

| Layer | Technology |
| --- | --- |
| Frontend (Web) | Next.js 14+ App Router, TypeScript, Tailwind, shadcn/ui |
| Frontend (Mobile, Phase 2) | React Native (Expo) |
| API Gateway | Kong / AWS API Gateway |
| Backend (core services) | NestJS (TypeScript) |
| Backend (enterprise integrations) | Spring Boot (Java) |
| Database | PostgreSQL 15+ (primary), Redis 7 (cache/sessions) |
| AI/LLM | Claude API + LangChain; prompt caching enabled |
| File Storage | AWS S3 (prod) / MinIO (local) |
| Search | Elasticsearch / OpenSearch (Phase 2) |
| Auth | Keycloak or Auth0 (decision D9) — SAML 2.0 + OIDC |
| Infrastructure | AWS (ECS/EKS), Terraform, GitHub Actions |
| Monitoring | Grafana + Prometheus + Sentry |

# 12. Security Overview

| Control | Standard | Status |
| --- | --- | --- |
| Tenant isolation | SOC 2 Type II | ● Enforced via hook + skill |
| PII stripped before Claude calls | Responsible AI / DPDP Act 2023 | ● Enforced via pre-edit hook |
| Audit log (append-only) | ISO 27001 A.12.4 | ● Designed; build Sprint 1 |
| RBAC with tenant-scoped permissions | Least Privilege | ● Designed |
| JWT short-expiry + refresh rotation | OWASP ASVS L2 | ● Designed |
| Encryption at rest (RDS + KMS) | NIST SP 800-175B | ● Planned Sprint 0 |
| TLS 1.3 on all endpoints | OWASP ASVS L2 | ● Planned Sprint 0 |
| SAST + dependency scan in CI | OWASP Testing Guide v4 | ● Planned Sprint 0 |

# 13. VAPT / Vulnerability Findings

Not yet run — internal scan scheduled Sprint 7, external pentest in Sprint 15 (Phase 2 close).

# 14. Functional Gaps Summary

| Phase | Effort (days) | Focus |
| --- | --- | --- |
| Hyper-MVP (W1–6) | ~95 | 6 features minimum for appraisal cycle |
| Phase 1 remainder (W7–16) | ~72 | Dashboards, SSO, notifications, reporting |
| Phase 2 (W17–32) | 165 | AI, peer review, HRMS, mobile, learning |
| Phase 3 (W33–48) | 150 | Multi-tenancy, billing, marketplace, scale |

# 15. Environment Access

| Environment | URL | Purpose |
| --- | --- | --- |
| Local | http://localhost:3000 | Each developer's machine |
| Dev | https://dev.skillforge.qualtech.internal (TBD) | Shared branch integration |
| Staging | https://staging.skillforge.qualtech.internal (TBD) | Pre-prod, UAT |
| Production | https://skillforge.qualtech.internal (TBD) | Qualtech workforce |

# 16. Effort Summary

| Metric | Value |
| --- | --- |
| Total team size (Phase 1) | 9–10 FTE |
| Phase 1 duration | 16 weeks (8 sprints of 2 weeks) |
| Phase 1 effort | 167 person-days |
| Hyper-MVP window | 6 weeks (3 sprints) |
| Hyper-MVP effort | ~95 person-days |
| Total programme duration | 48 weeks (Phase 1 + 2 + 3) |
| Total programme effort | ~482 person-days |

# 17. Commit Type Breakdown (planned)

| Type | Hyper-MVP est. | Phase 1 total | Phase 2 total |
| --- | --- | --- | --- |
| feat | ~45 | ~80 | ~85 |
| fix | ~15 | ~30 | ~35 |
| docs | ~8 | ~15 | ~20 |
| security | ~5 | ~10 | ~20 |
| test | ~15 | ~25 | ~40 |
| chore / refactor | ~12 | ~20 | ~25 |

# 18. References & Links

| Reference | Location |
| --- | --- |
| Strategic plan (source of truth) | SkillForge_AI_Project_Plan.docx |
| Build plan (this doc's Markdown) | BUILD_PLAN.md |
| Sprint 0 checklist | docs/SPRINT_0_CHECKLIST.md |
| Open decisions | OPEN_DECISIONS.md |
| Project memory index | ~/.claude/projects/-Users-aksatyam-SelfWork-SkillForge/memory/MEMORY.md |
| Project Claude guide | CLAUDE.md |
| Project-scoped skills | .claude/skills/ |
| Project hooks | .claude/hooks/ |
| Repository (after Sprint 0) | git@github.com:qualtech/skillforge.git (TBD) |
| Jira / Linear board | TBD in Sprint 0 |

## Prepared By

Ashish Kumar Satyam

TechDigital WishTree

For: Qualtech

Date: 2026-04-18

Classification: Internal — Confidential