PROJECT PLAN

AI-Powered Employee Skill

Assessment Platform

Internal Product Development | SaaS Platform

Codename: SkillForge AI

| Document | Project Plan v1.0 |
| --- | --- |
| Product Owner | Qualtech |
| Development | Qualtech Internal Engineering |
| Date | April 2026 |
| Classification | Internal — Confidential |

Table of Contents

1. Executive Summary	3

1.1 Product Vision	3

1.2 Key Objectives	3

2. Product Overview	4

2.1 Platform Modules	4

2.2 User Personas	4

3. Technical Architecture	6

3.1 Architecture Principles	6

3.2 Technology Stack	6

3.3 High-Level Architecture	7

4. Feature Roadmap & Phased Delivery	8

4.1 Phase 1: MVP (Weeks 1–8)	8

4.2 Phase 2: AI Intelligence + Advanced Features (Weeks 9–16)	10

4.3 Phase 3: SaaS & Scale (Weeks 17–24)	10

5. Team Structure & Resource Plan	12

5.1 Core Team (Phase 1 — MVP)	12

5.2 Sprint Cadence	12

6. Core Data Model	13

7. AI Integration Design	14

7.1 Artifact Analysis	14

7.2 Score Suggestion	14

7.3 Bias Detection	14

7.4 AI Governance Guardrails	14

8. Security & Compliance	15

9. Budget Estimation	16

10. Risks & Mitigation	17

11. Success Criteria	18

11.1 MVP Launch Criteria (Phase 1)	18

11.2 Product Success Metrics (6 Months Post-Launch)	18

12. Next Steps	19

# 1. Executive Summary

Qualtech has mandated organization-wide AI capability development, with AI adoption forming a key part of the upcoming appraisal cycle (April–June 2026). To operationalize this mandate at scale and sustain it beyond the initial assessment window, Qualtech requires a purpose-built platform that can assess, track, and develop AI skills across the entire workforce.

SkillForge AI is an AI-powered Employee Skill Assessment Platform designed to serve this exact need. It will function as the central system for defining AI competency expectations by role, conducting multi-dimensional assessments, tracking progress over time, generating analytics for leadership, and integrating with existing HR and performance management systems.

Beyond serving Qualtech’s internal needs, SkillForge AI is architected as a multi-tenant SaaS product that can be offered to other enterprises facing the same challenge — making it both an operational tool and a revenue opportunity.

## 1.1 Product Vision

"Enable every organization to measure, develop, and sustain AI capability across their workforce — fairly, continuously, and at scale."

## 1.2 Key Objectives

- Replace spreadsheet-based and manual AI skill tracking with a structured, automated platform

- Provide role-specific assessment workflows aligned with the AI Capability Maturity Model

- Deliver real-time dashboards for managers, HR, and leadership with actionable insights

- Integrate with existing HRMS and performance systems to feed AI capability scores into appraisals

- Build a scalable SaaS product that can be deployed to external clients

# 2. Product Overview

## 2.1 Platform Modules

| Module | Description | Key Features |
| --- | --- | --- |
| Competency Framework Engine | Define and manage AI maturity models, role-family mappings, and target levels. Supports multiple frameworks per organization. | Custom maturity levels; role-to-level mapping; versioning; bulk import/export; template library |
| Assessment Workflow | Conduct multi-dimensional assessments: self-assessment, manager evaluation, peer feedback, and artifact review — all in one flow. | Configurable assessment components; weighted scoring; evidence upload; deadline management; reminders |
| AI-Powered Evaluation | Use AI to assist managers in reviewing submitted artifacts, generating summary scores, and identifying skill gaps. | Artifact analysis (documents, code, prompts); AI-suggested scores; bias detection; consistency checks |
| Learning Recommendations | Based on assessment outcomes, recommend targeted training modules, use cases, and resources to close skill gaps. | Gap-to-content mapping; integration with LMS; personalized learning paths; progress tracking |
| Analytics & Dashboards | Real-time dashboards for employees, managers, HR, and C-suite with drill-down capability. | Individual scorecards; team heatmaps; function-level trends; org-wide maturity distribution; export to PDF/Excel |
| HRMS Integration | Bi-directional integration with existing HRMS and performance management systems. | API-based integration; score push to appraisal systems; employee data sync; SSO; role hierarchy sync |
| Admin & Configuration | Multi-tenant administration: org setup, role management, assessment cycle configuration, notification rules. | Tenant management; RBAC; assessment cycle lifecycle; email/notification templates; audit logs |

## 2.2 User Personas

- Employee: Completes self-assessments; uploads artifacts; views personal scorecard and learning recommendations; tracks progress.

- Manager: Sets team expectations; conducts evaluations; reviews AI-suggested scores; provides coaching notes; monitors team dashboard.

- HR / L&D Admin: Configures assessment cycles; manages frameworks; monitors org-wide analytics; generates appraisal-ready reports.

- AI Champion: Reviews artifacts across teams; validates AI-suggested scores; contributes to prompt/use-case libraries.

- Leadership / CXO: Views strategic dashboards; tracks org-wide AI readiness; makes investment and training decisions based on data.

# 3. Technical Architecture

## 3.1 Architecture Principles

- Multi-tenant SaaS from day one — data isolation at the tenant level

- API-first design — every feature accessible via documented REST APIs

- Modular microservices — independently deployable services per domain

- AI-native — LLM integration as a core service, not a bolt-on

- Cloud-native — containerized, auto-scaling, infrastructure-as-code

- Security-first — OWASP compliance, encryption at rest and in transit, RBAC, audit logging

## 3.2 Technology Stack

| Layer | Technology | Rationale |
| --- | --- | --- |
| Frontend (Web) | Next.js 14+ (React), TypeScript, Tailwind CSS, shadcn/ui | SSR for performance; type safety; rapid UI development; consistent design system |
| Frontend (Mobile) | React Native (Expo) | Cross-platform mobile access for assessments and dashboards; code sharing with web |
| API Gateway | Kong / AWS API Gateway | Rate limiting, auth, routing, API versioning, analytics |
| Backend Services | NestJS (TypeScript) / Spring Boot (Java) | NestJS for core services (speed); Spring Boot for enterprise integrations (HRMS, SSO) |
| Database | PostgreSQL (primary), Redis (cache/sessions) | ACID compliance; JSON support; proven at scale; fast caching layer |
| AI/LLM Service | Claude API (Anthropic) + LangChain | Best-in-class reasoning for artifact analysis; structured output; prompt chaining |
| File Storage | AWS S3 / MinIO | Artifact uploads; report storage; document processing pipeline |
| Search | Elasticsearch / OpenSearch | Full-text search across assessments, artifacts, and prompt libraries |
| Auth | Keycloak / Auth0 | SSO (SAML, OIDC); RBAC; multi-tenant identity management |
| Infrastructure | AWS (ECS/EKS), Terraform, GitHub Actions | Container orchestration; IaC; CI/CD pipelines |
| Monitoring | Grafana, Prometheus, Sentry | Observability; alerting; error tracking |

## 3.3 High-Level Architecture

The platform follows a layered architecture with clear separation of concerns:

- Presentation Layer: Next.js web app + React Native mobile app, communicating via REST/GraphQL APIs

- API Gateway: Authentication, rate limiting, request routing to backend microservices

- Service Layer: Independent microservices for Assessment, Framework, Analytics, AI Evaluation, Notification, Integration

- AI Layer: Dedicated LLM service wrapping Claude API via LangChain for artifact analysis, score suggestion, and gap detection

- Data Layer: PostgreSQL per-tenant schema isolation; Redis for sessions and caching; S3 for file storage

- Integration Layer: Webhook and API-based connectors for HRMS, LMS, SSO, and notification services

# 4. Feature Roadmap & Phased Delivery

The product is delivered in three phases, with each phase producing a usable, deployable release. Phase 1 (MVP) is designed to meet the immediate appraisal cycle need. Phases 2 and 3 add depth and SaaS scalability.

## 4.1 Phase 1: MVP (Weeks 1–8)

Goal: A functional platform that supports the current assessment cycle for 500+ employees.

| # | Feature | Priority | Sprint | Effort (Person-Days) |
| --- | --- | --- | --- | --- |
| 1 | User management + RBAC (Employee, Manager, HR Admin) | P0 | Sprint 1-2 | 15 |
| 2 | Competency Framework Engine (define maturity model, role mappings) | P0 | Sprint 1-2 | 12 |
| 3 | Self-Assessment module (questionnaire builder, submission) | P0 | Sprint 2-3 | 15 |
| 4 | Manager Assessment module (scoring UI, evidence review) | P0 | Sprint 3-4 | 18 |
| 5 | Artifact upload and management | P0 | Sprint 2-3 | 10 |
| 6 | Weighted composite scoring engine | P0 | Sprint 4 | 8 |
| 7 | Employee scorecard dashboard | P1 | Sprint 4-5 | 12 |
| 8 | Manager team dashboard | P1 | Sprint 5 | 10 |
| 9 | HR admin dashboard (org-wide view) | P1 | Sprint 5-6 | 12 |
| 10 | Assessment cycle lifecycle (create, open, close, lock) | P0 | Sprint 3 | 8 |
| 11 | Email notifications (reminders, deadlines, completion) | P1 | Sprint 4-5 | 6 |
| 12 | SSO integration (SAML/OIDC) | P1 | Sprint 6 | 8 |
| 13 | CSV/Excel export for appraisal integration | P0 | Sprint 6 | 5 |
| 14 | Basic reporting (completion rates, score distribution) | P1 | Sprint 6-7 | 8 |
| 15 | UAT, bug fixes, hardening | P0 | Sprint 7-8 | 20 |
|  | Phase 1 Total |  | 8 Sprints (16 weeks) | 167 |

## 4.2 Phase 2: AI Intelligence + Advanced Features (Weeks 9–16)

Goal: Add AI-powered evaluation, learning recommendations, and advanced analytics.

| # | Feature | Priority | Sprint | Effort (Person-Days) |
| --- | --- | --- | --- | --- |
| 16 | AI Artifact Analysis (document, code, prompt review via Claude API) | P0 | Sprint 9-10 | 20 |
| 17 | AI-Suggested Scores with confidence levels | P0 | Sprint 10-11 | 15 |
| 18 | Skill Gap Detection and visualization | P1 | Sprint 11 | 10 |
| 19 | Learning Path Recommendations engine | P1 | Sprint 11-12 | 12 |
| 20 | Peer Feedback module (360-degree input) | P0 | Sprint 9-10 | 12 |
| 21 | Prompt Library (org-wide, searchable, rated) | P1 | Sprint 12 | 10 |
| 22 | Advanced Analytics (heatmaps, trend analysis, cohort comparison) | P1 | Sprint 12-13 | 15 |
| 23 | HRMS API integration (bi-directional score sync) | P0 | Sprint 13-14 | 15 |
| 24 | LMS integration (training completion data pull) | P2 | Sprint 14 | 8 |
| 25 | Bias detection in manager scoring (statistical outlier analysis) | P1 | Sprint 14-15 | 10 |
| 26 | Mobile app (React Native — assessment + dashboard) | P1 | Sprint 13-15 | 20 |
| 27 | UAT, performance testing, security audit | P0 | Sprint 15-16 | 18 |
|  | Phase 2 Total |  | 8 Sprints (16 weeks) | 165 |

## 4.3 Phase 3: SaaS & Scale (Weeks 17–24)

Goal: Multi-tenant SaaS readiness, self-service onboarding, marketplace, and external client deployment.

- Multi-tenant data isolation and tenant provisioning

- Self-service organization onboarding and configuration wizard

- Subscription management and billing integration (Stripe/Razorpay)

- White-label customization (branding, domain mapping)

- Marketplace for assessment templates and prompt libraries

- API documentation portal (Swagger/Redoc) for third-party integrations

- SOC 2 / ISO 27001 compliance preparation

- Performance optimization for 10,000+ concurrent users

Phase 3 Estimated Effort: 150 person-days across 8 sprints

# 5. Team Structure & Resource Plan

## 5.1 Core Team (Phase 1 — MVP)

| Role | Count | Responsibilities | Skills Required |
| --- | --- | --- | --- |
| Product Owner | 1 | Roadmap, prioritization, stakeholder management, acceptance criteria | Domain understanding, product management, AI literacy |
| Tech Lead / Architect | 1 | Architecture decisions, code reviews, technical direction, DevOps setup | Full-stack expertise, system design, cloud architecture, AI/LLM integration |
| Senior Frontend Dev | 2 | Next.js web app, React Native mobile app, dashboard components | React/Next.js, TypeScript, Tailwind, charting libraries, responsive design |
| Senior Backend Dev | 2 | NestJS microservices, API design, database schema, integrations | NestJS/Node.js, PostgreSQL, REST API design, queue systems |
| AI/ML Engineer | 1 | LLM integration, prompt engineering, artifact analysis pipeline, evaluation logic | Claude/OpenAI API, LangChain, prompt engineering, NLP |
| UI/UX Designer | 1 | User research, wireframes, design system, prototypes, usability testing | Figma, design systems, enterprise SaaS UX, data visualization |
| QA Engineer | 1 | Test strategy, automated testing, UAT coordination, regression | Playwright/Cypress, API testing, performance testing |
| DevOps Engineer | 1 (shared) | CI/CD pipelines, infrastructure, monitoring, deployment automation | AWS, Terraform, Docker, GitHub Actions, Grafana |
| Total Team | 9-10 |  |  |

## 5.2 Sprint Cadence

- Sprint duration: 2 weeks

- Ceremonies: Sprint planning (Monday), daily standups (15 min), sprint review (Friday of Week 2), retrospective (bi-weekly)

- Demo cadence: End of every sprint to product owner and key stakeholders

- Release cadence: End of every 2 sprints (monthly) to staging; quarterly production releases

# 6. Core Data Model

The following tables represent the primary entities in the system. The actual schema will include additional audit columns, indexes, and relationship tables.

| Entity | Key Attributes | Relationships |
| --- | --- | --- |
| Organization (Tenant) | id, name, domain, subscription_plan, settings_json, created_at | Has many Users, Frameworks, Assessment Cycles |
| User | id, org_id, email, name, role_family, designation, manager_id, auth_provider_id | Belongs to Organization; has many Assessments, Artifacts |
| Competency Framework | id, org_id, name, version, maturity_levels_json, status | Belongs to Organization; has many Role Mappings |
| Role Mapping | id, framework_id, role_family, target_level, assessment_criteria_json | Belongs to Framework |
| Assessment Cycle | id, org_id, framework_id, name, start_date, end_date, status | Belongs to Organization; has many Assessments |
| Assessment | id, cycle_id, user_id, self_score, manager_score, peer_score, ai_score, composite_score, status | Belongs to Cycle and User; has many Artifacts, Peer Reviews |
| Artifact | id, assessment_id, user_id, file_url, artifact_type, ai_analysis_json, created_at | Belongs to Assessment and User |
| Peer Review | id, assessment_id, reviewer_id, ratings_json, comments, submitted_at | Belongs to Assessment; reviewer is a User |
| Learning Recommendation | id, assessment_id, skill_gap, recommended_resource, resource_type, priority | Belongs to Assessment |
| Prompt Library Entry | id, org_id, author_id, title, prompt_text, category, rating, usage_count | Belongs to Organization and User |

# 7. AI Integration Design

AI is not a feature layer in SkillForge — it is a core service that powers three critical capabilities.

## 7.1 Artifact Analysis

When an employee uploads a work artifact (document, code file, presentation, or prompt), the AI service analyzes it to determine:

- Evidence of AI tool usage in the creation process

- Quality assessment relative to role expectations

- Complexity and sophistication of AI application

- Comparison with baseline (pre-AI) outputs if available

Implementation: Claude API via LangChain. Each artifact type has a specialized prompt chain. Analysis results are stored as structured JSON and surfaced to managers as suggested evidence ratings.

## 7.2 Score Suggestion

Based on self-assessment responses, artifact analysis results, and peer feedback data, the AI service generates a suggested composite score with confidence levels. This is presented to the manager as a starting point, not a final score. The manager always retains override authority.

## 7.3 Bias Detection

The platform monitors scoring patterns across managers to detect statistical outliers — managers who consistently score higher or lower than organizational norms, or who show significant variance across demographic groups. Flagged patterns are surfaced to HR for calibration review.

## 7.4 AI Governance Guardrails

- All AI-generated scores are clearly labeled as suggestions, never auto-applied

- Manager override is logged with rationale for audit trail

- AI analysis is explainable — every score suggestion includes reasoning

- No employee data is used for model training — all API calls are stateless

- Data residency compliance: tenant-level configuration for API routing

# 8. Security & Compliance

| Area | Approach | Standard/Framework |
| --- | --- | --- |
| Authentication | SSO via SAML 2.0 / OIDC; MFA enforcement; session management with Redis | OWASP ASVS Level 2 |
| Authorization | RBAC with tenant-scoped permissions; resource-level access control | Principle of Least Privilege |
| Data Encryption | AES-256 at rest; TLS 1.3 in transit; field-level encryption for PII | NIST SP 800-175B |
| Data Isolation | Schema-per-tenant in PostgreSQL; tenant context enforced at API layer | SOC 2 Type II |
| Audit Logging | Immutable audit log for all assessment actions; tamper-evident storage | ISO 27001 A.12.4 |
| API Security | Rate limiting; input validation; JWT with short expiry; CORS policy | OWASP API Top 10 |
| VAPT | Quarterly vulnerability assessment; annual penetration testing | OWASP Testing Guide v4 |
| Privacy | DPDP Act 2023 compliance; data minimization; consent management; right to erasure | DPDP Act 2023 / GDPR alignment |
| AI Data Handling | No training on user data; stateless API calls; data classification enforcement | Responsible AI principles |

# 9. Budget Estimation

The following is an indicative budget for the MVP phase (Phase 1, 16 weeks). Costs are based on internal team rates. Actual costs will depend on resource allocation and infrastructure choices.

| Cost Category | Details | Monthly (Est.) | Phase 1 Total (4 months) |
| --- | --- | --- | --- |
| Engineering Team (9 FTEs) | Loaded cost per FTE | Per internal rates | Per internal rates |
| Cloud Infrastructure (AWS) | ECS/EKS, RDS, S3, ElastiCache, CloudFront | ₹1.5–2.5L | ₹6–10L |
| AI API Costs (Claude) | Artifact analysis + score suggestion (est. 50K API calls/month at scale) | ₹1–2L | ₹4–8L |
| Third-Party Services | Auth0/Keycloak, monitoring, email (SendGrid), search | ₹50K–1L | ₹2–4L |
| Design & UX Tools | Figma, user testing tools | ₹30K | ₹1.2L |
| Security & Compliance | VAPT tools, SSL certificates, audit tooling | ₹50K | ₹2L |

Note: Engineering team costs are excluded from the table above as they follow internal resource allocation. Infrastructure and service costs are estimated based on AWS India (Mumbai) region pricing and may vary based on usage patterns.

# 10. Risks & Mitigation

| Risk | Severity | Mitigation | Owner |
| --- | --- | --- | --- |
| MVP timeline too tight for appraisal cycle | High | Prioritize P0 features ruthlessly; deploy assessment + scoring first; add dashboards incrementally | Product Owner + Tech Lead |
| AI hallucination in artifact analysis | High | Human-in-the-loop (manager review mandatory); confidence thresholds; fallback to manual scoring | AI Engineer + Product Owner |
| HRMS integration complexity | Medium | Phase 1 uses CSV export; API integration in Phase 2; early discovery of HRMS API capabilities | Tech Lead + IT |
| Employee resistance to AI-scored assessments | Medium | AI scores are suggestions only; transparency in methodology; manager override always available | HR + Product Owner |
| Data privacy concerns with AI processing | High | Stateless API calls; no training on user data; tenant-level data residency; DPDP Act compliance | Security Lead + Legal |
| Scope creep during MVP | Medium | Strict P0/P1/P2 prioritization; change request process; sprint commitment discipline | Product Owner + Scrum Master |
| Key person dependency | Medium | Documentation-first culture; pair programming; knowledge transfer sessions; cross-training | Tech Lead + Engineering Manager |

# 11. Success Criteria

## 11.1 MVP Launch Criteria (Phase 1)

- 500+ employees can complete self-assessments through the platform

- Managers can conduct evaluations and produce composite scores for their direct reports

- HR can export assessment scores in appraisal-ready format

- System handles concurrent load of 200+ users without degradation

- All P0 features delivered, tested, and signed off

- Security audit completed with no critical or high findings

## 11.2 Product Success Metrics (6 Months Post-Launch)

- 90%+ assessment completion rate across the organization

- Manager satisfaction score of 4+/5 for assessment workflow usability

- 75%+ of managers use AI-suggested scores as a reference point

- 50% reduction in time spent on AI capability assessment vs. manual process

- Platform readiness for first external client deployment (Phase 3)

# 12. Next Steps

The following actions are recommended to move from plan to execution:

- Stakeholder Alignment: Present this plan to engineering leadership, HR, and product stakeholders for sign-off on scope, timeline, and resource allocation.

- Team Assembly: Identify and allocate the 9-10 member core team. Prioritize Tech Lead and Senior Backend Dev hiring/allocation first.

- Architecture Workshop (2 days): Tech Lead conducts detailed architecture design, finalizes technology choices, sets up development infrastructure.

- Sprint 0 (1 week): Repository setup, CI/CD pipeline, database provisioning, design system foundation, project management tooling.

- Design Sprint (Week 1-2): UI/UX designer produces wireframes and prototypes for core assessment workflows; user validation with 5-10 employees and managers.

- Sprint 1 Kickoff: Begin development with user management + competency framework engine.

Given the appraisal timeline constraint (assessments by end of May), an accelerated MVP targeting core assessment and scoring features in 8 weeks is recommended. Dashboard and analytics features can follow in a fast-follow release.

SkillForge AI

Built by Qualtech. Powered by AI. Designed for People.